## Sheet1
plot_id | project_id | survey_number | land_area_hectares | owner_count | ownership_conflict | legal_dispute | compensation_completion_percent | documentation_completion_percent | rr_required | rr_completion_percent | possession_percent | stakeholder_response_rate | parcel_risk_score | parcel_risk_level | Parcel_Risk_Score | Parcel_Risk_Level | Risk_Reasons | Recommended_Action
P10002-PL-001 | P10002 | S-89936 | 1.91 | 5 | 0 | 0 | 32 | 64 | 1 | 22 | 17 | 35 |  |  | 70 | CRITICAL | Compensation completion is critically low ¦ R&R progress is critically low ¦ Land possession is significantly incomplete ¦ Very low stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-002 | P10002 | S-78640 | 7.51 | 5 | 0 | 0 | 42 | 66 | 1 | 46 | 21 | 45 |  |  | 57 | HIGH | Compensation is only partially completed ¦ R&R is partially completed ¦ Land possession is significantly incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-003 | P10002 | S-74773 | 4.19 | 4 | 0 | 0 | 22 | 56 | 1 | 51 | 37 | 54 |  |  | 62 | HIGH | Compensation completion is critically low ¦ Documentation is partially completed ¦ R&R is partially completed ¦ Land possession is partially incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-004 | P10002 | S-34764 | 1.81 | 4 | 0 | 0 | 37 | 49 | 1 | 20 | 19 | 71 |  |  | 68 | HIGH | Compensation completion is critically low ¦ Documentation is partially completed ¦ R&R progress is critically low ¦ Land possession is significantly incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-005 | P10002 | S-45564 | 5.39 | 4 | 0 | 0 | 32 | 47 | 1 | 36 | 39 | 65 |  |  | 63 | HIGH | Compensation completion is critically low ¦ Documentation is partially completed ¦ R&R progress is critically low ¦ Land possession is partially incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-006 | P10002 | S-39797 | 2.74 | 1 | 0 | 0 | 47 | 36 | 1 | 48 | 36 | 54 |  |  | 62 | HIGH | Compensation is only partially completed ¦ Documentation is critically incomplete ¦ R&R is partially completed ¦ Land possession is partially incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-007 | P10002 | S-77017 | 6.5 | 4 | 0 | 0 | 48 | 50 | 1 | 57 | 31 | 63 |  |  | 53 | HIGH | Compensation is only partially completed ¦ Documentation is partially completed ¦ R&R is partially completed ¦ Land possession is partially incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-008 | P10002 | S-46080 | 6.07 | 3 | 0 | 0 | 44 | 34 | 0 | 100 | 24 | 45 |  |  | 57 | HIGH | Compensation is only partially completed ¦ Documentation is critically incomplete ¦ Land possession is significantly incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-009 | P10002 | S-35190 | 4.44 | 3 | 0 | 0 | 58 | 31 | 1 | 46 | 44 | 69 |  |  | 58 | HIGH | Compensation is only partially completed ¦ Documentation is critically incomplete ¦ R&R is partially completed ¦ Land possession is partially incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-010 | P10002 | S-20594 | 1.88 | 5 | 0 | 0 | 40 | 51 | 1 | 43 | 6 | 71 |  |  | 58 | HIGH | Compensation is only partially completed ¦ Documentation is partially completed ¦ R&R is partially completed ¦ Land possession is significantly incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-011 | P10002 | S-77245 | 0.92 | 1 | 0 | 0 | 31 | 54 | 0 | 100 | 10 | 70 |  |  | 53 | HIGH | Compensation completion is critically low ¦ Documentation is partially completed ¦ Land possession is significantly incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-012 | P10002 | S-94370 | 6.74 | 1 | 0 | 0 | 22 | 32 | 0 | 100 | 30 | 59 |  |  | 57 | HIGH | Compensation completion is critically low ¦ Documentation is critically incomplete ¦ Land possession is partially incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-013 | P10002 | S-14820 | 2.74 | 3 | 0 | 0 | 54 | 37 | 0 | 100 | 23 | 61 |  |  | 53 | HIGH | Compensation is only partially completed ¦ Documentation is critically incomplete ¦ Land possession is significantly incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-014 | P10002 | S-92617 | 5.76 | 5 | 1 | 0 | 49 | 60 | 1 | 28 | 35 | 62 |  |  | 68 | HIGH | Ownership conflict ¦ Compensation is only partially completed ¦ R&R progress is critically low ¦ Land possession is partially incomplete | Verify ownership using revenue records, survey records and registration records before proceeding with acquisition. ¦ Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-015 | P10002 | S-27627 | 3.34 | 4 | 0 | 0 | 38 | 39 | 0 | 100 | 17 | 69 |  |  | 58 | HIGH | Compensation completion is critically low ¦ Documentation is critically incomplete ¦ Land possession is significantly incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-016 | P10002 | S-18150 | 4.68 | 4 | 0 | 0 | 54 | 32 | 0 | 100 | 43 | 55 |  |  | 52 | HIGH | Compensation is only partially completed ¦ Documentation is critically incomplete ¦ Land possession is partially incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-017 | P10002 | S-43409 | 0.64 | 1 | 0 | 0 | 15 | 52 | 0 | 100 | 11 | 38 |  |  | 60 | HIGH | Compensation completion is critically low ¦ Documentation is partially completed ¦ Land possession is significantly incomplete ¦ Very low stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-018 | P10002 | S-68820 | 7.28 | 5 | 0 | 0 | 33 | 45 | 1 | 21 | 32 | 75 |  |  | 63 | HIGH | Compensation completion is critically low ¦ Documentation is partially completed ¦ R&R progress is critically low ¦ Land possession is partially incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-019 | P10002 | S-94111 | 1.59 | 5 | 0 | 0 | 29 | 38 | 1 | 41 | 38 | 64 |  |  | 63 | HIGH | Compensation completion is critically low ¦ Documentation is critically incomplete ¦ R&R is partially completed ¦ Land possession is partially incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-020 | P10002 | S-34194 | 6.91 | 4 | 1 | 0 | 52 | 56 | 0 | 100 | 40 | 47 |  |  | 62 | HIGH | Ownership conflict ¦ Compensation is only partially completed ¦ Documentation is partially completed ¦ Land possession is partially incomplete ¦ Moderate stakeholder response | Verify ownership using revenue records, survey records and registration records before proceeding with acquisition. ¦ Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-021 | P10002 | S-48662 | 7.39 | 3 | 0 | 0 | 54 | 51 | 1 | 58 | 43 | 44 |  |  | 57 | HIGH | Compensation is only partially completed ¦ Documentation is partially completed ¦ R&R is partially completed ¦ Land possession is partially incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-022 | P10002 | S-12851 | 4.4 | 2 | 0 | 0 | 51 | 45 | 1 | 24 | 50 | 41 |  |  | 55 | HIGH | Compensation is only partially completed ¦ Documentation is partially completed ¦ R&R progress is critically low ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-023 | P10002 | S-32083 | 0.78 | 4 | 1 | 0 | 15 | 40 | 0 | 100 | 42 | 63 |  |  | 63 | HIGH | Ownership conflict ¦ Compensation completion is critically low ¦ Documentation is partially completed ¦ Land possession is partially incomplete | Verify ownership using revenue records, survey records and registration records before proceeding with acquisition. ¦ Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-024 | P10002 | S-52346 | 0.66 | 4 | 0 | 0 | 30 | 32 | 0 | 100 | 41 | 72 |  |  | 53 | HIGH | Compensation completion is critically low ¦ Documentation is critically incomplete ¦ Land possession is partially incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-025 | P10002 | S-85988 | 2.05 | 2 | 0 | 0 | 56 | 35 | 1 | 54 | 27 | 47 |  |  | 67 | HIGH | Compensation is only partially completed ¦ Documentation is critically incomplete ¦ R&R is partially completed ¦ Land possession is significantly incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-026 | P10002 | S-95022 | 6.3 | 4 | 0 | 0 | 47 | 54 | 1 | 50 | 42 | 57 |  |  | 57 | HIGH | Compensation is only partially completed ¦ Documentation is partially completed ¦ R&R is partially completed ¦ Land possession is partially incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-027 | P10002 | S-17084 | 1.81 | 5 | 1 | 0 | 41 | 50 | 0 | 100 | 6 | 74 |  |  | 63 | HIGH | Ownership conflict ¦ Compensation is only partially completed ¦ Documentation is partially completed ¦ Land possession is significantly incomplete | Verify ownership using revenue records, survey records and registration records before proceeding with acquisition. ¦ Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-028 | P10002 | S-80564 | 1.46 | 1 | 0 | 0 | 34 | 35 | 1 | 35 | 32 | 65 |  |  | 68 | HIGH | Compensation completion is critically low ¦ Documentation is critically incomplete ¦ R&R progress is critically low ¦ Land possession is partially incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-029 | P10002 | S-50716 | 5.61 | 2 | 0 | 0 | 58 | 65 | 1 | 31 | 36 | 46 |  |  | 57 | HIGH | Compensation is only partially completed ¦ R&R progress is critically low ¦ Land possession is partially incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-030 | P10002 | S-92350 | 6.37 | 3 | 0 | 0 | 33 | 43 | 0 | 100 | 12 | 71 |  |  | 53 | HIGH | Compensation completion is critically low ¦ Documentation is partially completed ¦ Land possession is significantly incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-031 | P10002 | S-30689 | 2.93 | 5 | 0 | 0 | 37 | 68 | 1 | 47 | 15 | 72 |  |  | 58 | HIGH | Compensation completion is critically low ¦ R&R is partially completed ¦ Land possession is significantly incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-032 | P10002 | S-19672 | 3.93 | 4 | 0 | 0 | 57 | 40 | 1 | 44 | 33 | 42 |  |  | 57 | HIGH | Compensation is only partially completed ¦ Documentation is partially completed ¦ R&R is partially completed ¦ Land possession is partially incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-033 | P10002 | S-84120 | 2.84 | 5 | 0 | 0 | 41 | 39 | 1 | 38 | 32 | 72 |  |  | 63 | HIGH | Compensation is only partially completed ¦ Documentation is critically incomplete ¦ R&R progress is critically low ¦ Land possession is partially incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-034 | P10002 | S-69830 | 5.2 | 1 | 0 | 0 | 53 | 64 | 0 | 100 | 38 | 35 |  |  | 45 | MEDIUM | Compensation is only partially completed ¦ Land possession is partially incomplete ¦ Very low stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-035 | P10002 | S-33734 | 3.89 | 4 | 0 | 0 | 51 | 52 | 0 | 100 | 32 | 35 |  |  | 50 | HIGH | Compensation is only partially completed ¦ Documentation is partially completed ¦ Land possession is partially incomplete ¦ Very low stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-036 | P10002 | S-91351 | 4.72 | 3 | 0 | 0 | 22 | 52 | 0 | 100 | 9 | 44 |  |  | 57 | HIGH | Compensation completion is critically low ¦ Documentation is partially completed ¦ Land possession is significantly incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-037 | P10002 | S-39388 | 0.71 | 5 | 0 | 0 | 48 | 54 | 1 | 55 | 16 | 59 |  |  | 62 | HIGH | Compensation is only partially completed ¦ Documentation is partially completed ¦ R&R is partially completed ¦ Land possession is significantly incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-038 | P10002 | S-57993 | 2.29 | 1 | 0 | 0 | 19 | 42 | 0 | 100 | 44 | 48 |  |  | 52 | HIGH | Compensation completion is critically low ¦ Documentation is partially completed ¦ Land possession is partially incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-039 | P10002 | S-97204 | 2.3 | 2 | 0 | 0 | 34 | 43 | 0 | 100 | 37 | 53 |  |  | 52 | HIGH | Compensation completion is critically low ¦ Documentation is partially completed ¦ Land possession is partially incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-040 | P10002 | S-21790 | 7.58 | 5 | 0 | 0 | 54 | 44 | 0 | 100 | 39 | 39 |  |  | 50 | HIGH | Compensation is only partially completed ¦ Documentation is partially completed ¦ Land possession is partially incomplete ¦ Very low stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-041 | P10002 | S-96168 | 5.81 | 5 | 0 | 0 | 42 | 34 | 0 | 100 | 47 | 56 |  |  | 52 | HIGH | Compensation is only partially completed ¦ Documentation is critically incomplete ¦ Land possession is partially incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-042 | P10002 | S-94961 | 7.72 | 1 | 0 | 0 | 21 | 64 | 1 | 55 | 45 | 37 |  |  | 60 | HIGH | Compensation completion is critically low ¦ R&R is partially completed ¦ Land possession is partially incomplete ¦ Very low stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-043 | P10002 | S-16983 | 5.53 | 5 | 1 | 0 | 27 | 60 | 1 | 43 | 23 | 47 |  |  | 77 | CRITICAL | Ownership conflict ¦ Compensation completion is critically low ¦ R&R is partially completed ¦ Land possession is significantly incomplete ¦ Moderate stakeholder response | Verify ownership using revenue records, survey records and registration records before proceeding with acquisition. ¦ Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-044 | P10002 | S-44241 | 6.18 | 2 | 0 | 0 | 48 | 63 | 1 | 23 | 20 | 59 |  |  | 62 | HIGH | Compensation is only partially completed ¦ R&R progress is critically low ¦ Land possession is significantly incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-045 | P10002 | S-57904 | 6.09 | 3 | 0 | 0 | 19 | 66 | 1 | 59 | 5 | 45 |  |  | 62 | HIGH | Compensation completion is critically low ¦ R&R is partially completed ¦ Land possession is significantly incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-046 | P10002 | S-69969 | 7.45 | 2 | 0 | 0 | 27 | 48 | 1 | 39 | 49 | 49 |  |  | 67 | HIGH | Compensation completion is critically low ¦ Documentation is partially completed ¦ R&R progress is critically low ¦ Land possession is partially incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-047 | P10002 | S-27912 | 5.97 | 3 | 0 | 0 | 32 | 30 | 1 | 30 | 15 | 71 |  |  | 73 | CRITICAL | Compensation completion is critically low ¦ Documentation is critically incomplete ¦ R&R progress is critically low ¦ Land possession is significantly incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-048 | P10002 | S-23100 | 6.29 | 4 | 0 | 0 | 22 | 38 | 1 | 23 | 22 | 74 |  |  | 73 | CRITICAL | Compensation completion is critically low ¦ Documentation is critically incomplete ¦ R&R progress is critically low ¦ Land possession is significantly incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-049 | P10002 | S-14456 | 1.82 | 5 | 0 | 0 | 56 | 52 | 1 | 40 | 8 | 74 |  |  | 58 | HIGH | Compensation is only partially completed ¦ Documentation is partially completed ¦ R&R is partially completed ¦ Land possession is significantly incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-050 | P10002 | S-81069 | 7.37 | 4 | 0 | 0 | 15 | 67 | 0 | 100 | 16 | 70 |  |  | 48 | MEDIUM | Compensation completion is critically low ¦ Land possession is significantly incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-051 | P10002 | S-52264 | 2.53 | 4 | 0 | 0 | 53 | 60 | 0 | 100 | 48 | 56 |  |  | 42 | MEDIUM | Compensation is only partially completed ¦ Land possession is partially incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-052 | P10002 | S-66907 | 1.38 | 3 | 0 | 0 | 40 | 56 | 1 | 34 | 29 | 66 |  |  | 63 | HIGH | Compensation is only partially completed ¦ Documentation is partially completed ¦ R&R progress is critically low ¦ Land possession is significantly incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-053 | P10002 | S-73928 | 3.09 | 5 | 0 | 0 | 45 | 38 | 1 | 57 | 14 | 45 |  |  | 67 | HIGH | Compensation is only partially completed ¦ Documentation is critically incomplete ¦ R&R is partially completed ¦ Land possession is significantly incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-054 | P10002 | S-85878 | 4.23 | 4 | 0 | 0 | 15 | 51 | 0 | 100 | 31 | 70 |  |  | 48 | MEDIUM | Compensation completion is critically low ¦ Documentation is partially completed ¦ Land possession is partially incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-055 | P10002 | S-98240 | 2.06 | 1 | 0 | 1 | 52 | 45 | 1 | 24 | 46 | 67 |  |  | 78 | CRITICAL | Pending legal dispute ¦ Compensation is only partially completed ¦ Documentation is partially completed ¦ R&R progress is critically low ¦ Land possession is partially incomplete | Escalate the pending legal dispute for priority legal review and establish a defined resolution timeline. ¦ Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-056 | P10002 | S-44822 | 3.92 | 2 | 0 | 0 | 53 | 63 | 0 | 100 | 23 | 67 |  |  | 43 | MEDIUM | Compensation is only partially completed ¦ Land possession is significantly incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-057 | P10002 | S-34886 | 3.63 | 4 | 0 | 0 | 28 | 49 | 0 | 100 | 37 | 71 |  |  | 48 | MEDIUM | Compensation completion is critically low ¦ Documentation is partially completed ¦ Land possession is partially incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-058 | P10002 | S-17319 | 0.77 | 1 | 0 | 1 | 49 | 64 | 1 | 33 | 10 | 44 |  |  | 82 | CRITICAL | Pending legal dispute ¦ Compensation is only partially completed ¦ R&R progress is critically low ¦ Land possession is significantly incomplete ¦ Moderate stakeholder response | Escalate the pending legal dispute for priority legal review and establish a defined resolution timeline. ¦ Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-059 | P10002 | S-58893 | 2.31 | 5 | 0 | 0 | 60 | 56 | 0 | 100 | 37 | 64 |  |  | 36 | MEDIUM | Documentation is partially completed ¦ Land possession is partially incomplete | Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-060 | P10002 | S-34886 | 0.7 | 3 | 0 | 0 | 41 | 58 | 1 | 36 | 47 | 56 |  |  | 62 | HIGH | Compensation is only partially completed ¦ Documentation is partially completed ¦ R&R progress is critically low ¦ Land possession is partially incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-061 | P10002 | S-52528 | 2.76 | 2 | 0 | 0 | 27 | 45 | 1 | 42 | 48 | 73 |  |  | 58 | HIGH | Compensation completion is critically low ¦ Documentation is partially completed ¦ R&R is partially completed ¦ Land possession is partially incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-062 | P10002 | S-25067 | 5.43 | 2 | 0 | 0 | 43 | 41 | 1 | 55 | 50 | 73 |  |  | 46 | MEDIUM | Compensation is only partially completed ¦ Documentation is partially completed ¦ R&R is partially completed | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan.
P10002-PL-063 | P10002 | S-22229 | 7.01 | 1 | 0 | 0 | 16 | 35 | 0 | 100 | 49 | 73 |  |  | 53 | HIGH | Compensation completion is critically low ¦ Documentation is critically incomplete ¦ Land possession is partially incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-064 | P10002 | S-71906 | 6.24 | 1 | 0 | 0 | 32 | 53 | 0 | 100 | 33 | 61 |  |  | 48 | MEDIUM | Compensation completion is critically low ¦ Documentation is partially completed ¦ Land possession is partially incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-065 | P10002 | S-80537 | 1.57 | 1 | 1 | 0 | 35 | 46 | 1 | 57 | 30 | 65 |  |  | 73 | CRITICAL | Ownership conflict ¦ Compensation completion is critically low ¦ Documentation is partially completed ¦ R&R is partially completed ¦ Land possession is partially incomplete | Verify ownership using revenue records, survey records and registration records before proceeding with acquisition. ¦ Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-066 | P10002 | S-72372 | 1.92 | 4 | 0 | 0 | 41 | 70 | 0 | 100 | 11 | 63 |  |  | 43 | MEDIUM | Compensation is only partially completed ¦ Land possession is significantly incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-067 | P10002 | S-31391 | 3.55 | 5 | 0 | 0 | 35 | 32 | 0 | 100 | 13 | 63 |  |  | 58 | HIGH | Compensation completion is critically low ¦ Documentation is critically incomplete ¦ Land possession is significantly incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-068 | P10002 | S-91886 | 3.59 | 4 | 0 | 0 | 58 | 51 | 1 | 58 | 27 | 73 |  |  | 58 | HIGH | Compensation is only partially completed ¦ Documentation is partially completed ¦ R&R is partially completed ¦ Land possession is significantly incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-069 | P10002 | S-99566 | 1.79 | 2 | 0 | 0 | 58 | 34 | 0 | 100 | 7 | 58 |  |  | 57 | HIGH | Compensation is only partially completed ¦ Documentation is critically incomplete ¦ Land possession is significantly incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-070 | P10002 | S-24284 | 2.5 | 5 | 0 | 0 | 35 | 41 | 1 | 50 | 27 | 38 |  |  | 70 | CRITICAL | Compensation completion is critically low ¦ Documentation is partially completed ¦ R&R is partially completed ¦ Land possession is significantly incomplete ¦ Very low stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-071 | P10002 | S-42295 | 3.24 | 4 | 0 | 0 | 25 | 62 | 0 | 100 | 43 | 75 |  |  | 43 | MEDIUM | Compensation completion is critically low ¦ Land possession is partially incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-072 | P10002 | S-85894 | 1.83 | 5 | 0 | 0 | 21 | 48 | 0 | 100 | 23 | 54 |  |  | 57 | HIGH | Compensation completion is critically low ¦ Documentation is partially completed ¦ Land possession is significantly incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-073 | P10002 | S-53490 | 0.8 | 1 | 0 | 0 | 56 | 61 | 1 | 39 | 12 | 72 |  |  | 58 | HIGH | Compensation is only partially completed ¦ R&R progress is critically low ¦ Land possession is significantly incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-074 | P10002 | S-13116 | 3.46 | 1 | 0 | 0 | 29 | 60 | 1 | 53 | 24 | 68 |  |  | 58 | HIGH | Compensation completion is critically low ¦ R&R is partially completed ¦ Land possession is significantly incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-075 | P10002 | S-32061 | 5.67 | 5 | 0 | 0 | 25 | 55 | 0 | 100 | 8 | 68 |  |  | 53 | HIGH | Compensation completion is critically low ¦ Documentation is partially completed ¦ Land possession is significantly incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-076 | P10002 | S-38288 | 2.69 | 1 | 0 | 1 | 32 | 46 | 0 | 100 | 41 | 48 |  |  | 72 | CRITICAL | Pending legal dispute ¦ Compensation completion is critically low ¦ Documentation is partially completed ¦ Land possession is partially incomplete ¦ Moderate stakeholder response | Escalate the pending legal dispute for priority legal review and establish a defined resolution timeline. ¦ Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-077 | P10002 | S-54430 | 3.63 | 4 | 0 | 0 | 21 | 48 | 0 | 100 | 40 | 40 |  |  | 52 | HIGH | Compensation completion is critically low ¦ Documentation is partially completed ¦ Land possession is partially incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-078 | P10002 | S-80541 | 4.48 | 1 | 0 | 0 | 37 | 44 | 0 | 100 | 12 | 38 |  |  | 60 | HIGH | Compensation completion is critically low ¦ Documentation is partially completed ¦ Land possession is significantly incomplete ¦ Very low stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-079 | P10002 | S-39400 | 7.13 | 4 | 0 | 0 | 53 | 42 | 0 | 100 | 8 | 72 |  |  | 48 | MEDIUM | Compensation is only partially completed ¦ Documentation is partially completed ¦ Land possession is significantly incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-080 | P10002 | S-86841 | 3.51 | 3 | 0 | 0 | 24 | 36 | 1 | 43 | 28 | 49 |  |  | 72 | CRITICAL | Compensation completion is critically low ¦ Documentation is critically incomplete ¦ R&R is partially completed ¦ Land possession is significantly incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-081 | P10002 | S-99543 | 7.51 | 2 | 0 | 0 | 16 | 59 | 0 | 100 | 23 | 69 |  |  | 53 | HIGH | Compensation completion is critically low ¦ Documentation is partially completed ¦ Land possession is significantly incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-082 | P10002 | S-18547 | 1.71 | 1 | 0 | 0 | 43 | 44 | 1 | 31 | 24 | 73 |  |  | 63 | HIGH | Compensation is only partially completed ¦ Documentation is partially completed ¦ R&R progress is critically low ¦ Land possession is significantly incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-083 | P10002 | S-58154 | 7.53 | 1 | 0 | 0 | 21 | 50 | 1 | 54 | 7 | 37 |  |  | 70 | CRITICAL | Compensation completion is critically low ¦ Documentation is partially completed ¦ R&R is partially completed ¦ Land possession is significantly incomplete ¦ Very low stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-084 | P10002 | S-10995 | 5.18 | 3 | 0 | 0 | 16 | 54 | 1 | 27 | 47 | 37 |  |  | 70 | CRITICAL | Compensation completion is critically low ¦ Documentation is partially completed ¦ R&R progress is critically low ¦ Land possession is partially incomplete ¦ Very low stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-085 | P10002 | S-50588 | 3.14 | 2 | 1 | 0 | 37 | 33 | 0 | 100 | 33 | 50 |  |  | 72 | CRITICAL | Ownership conflict ¦ Compensation completion is critically low ¦ Documentation is critically incomplete ¦ Land possession is partially incomplete ¦ Moderate stakeholder response | Verify ownership using revenue records, survey records and registration records before proceeding with acquisition. ¦ Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-086 | P10002 | S-15027 | 0.96 | 4 | 0 | 0 | 49 | 46 | 0 | 100 | 45 | 48 |  |  | 47 | MEDIUM | Compensation is only partially completed ¦ Documentation is partially completed ¦ Land possession is partially incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-087 | P10002 | S-87258 | 4.56 | 2 | 0 | 0 | 38 | 59 | 1 | 57 | 29 | 41 |  |  | 67 | HIGH | Compensation completion is critically low ¦ Documentation is partially completed ¦ R&R is partially completed ¦ Land possession is significantly incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-088 | P10002 | S-86280 | 4.4 | 2 | 0 | 0 | 40 | 68 | 1 | 37 | 14 | 57 |  |  | 62 | HIGH | Compensation is only partially completed ¦ R&R progress is critically low ¦ Land possession is significantly incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-089 | P10002 | S-84862 | 4.13 | 3 | 0 | 0 | 39 | 37 | 0 | 100 | 16 | 40 |  |  | 62 | HIGH | Compensation completion is critically low ¦ Documentation is critically incomplete ¦ Land possession is significantly incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-090 | P10002 | S-53692 | 1.97 | 1 | 1 | 0 | 40 | 41 | 0 | 100 | 31 | 71 |  |  | 58 | HIGH | Ownership conflict ¦ Compensation is only partially completed ¦ Documentation is partially completed ¦ Land possession is partially incomplete | Verify ownership using revenue records, survey records and registration records before proceeding with acquisition. ¦ Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-091 | P10002 | S-22750 | 2.13 | 2 | 0 | 0 | 42 | 45 | 0 | 100 | 39 | 41 |  |  | 47 | MEDIUM | Compensation is only partially completed ¦ Documentation is partially completed ¦ Land possession is partially incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-092 | P10002 | S-63201 | 7.77 | 5 | 0 | 0 | 50 | 58 | 0 | 100 | 5 | 57 |  |  | 52 | HIGH | Compensation is only partially completed ¦ Documentation is partially completed ¦ Land possession is significantly incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-093 | P10002 | S-66998 | 1.11 | 3 | 0 | 0 | 60 | 32 | 1 | 58 | 36 | 41 |  |  | 55 | HIGH | Documentation is critically incomplete ¦ R&R is partially completed ¦ Land possession is partially incomplete ¦ Moderate stakeholder response | Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-094 | P10002 | S-38827 | 4.45 | 5 | 0 | 0 | 28 | 59 | 0 | 100 | 19 | 58 |  |  | 57 | HIGH | Compensation completion is critically low ¦ Documentation is partially completed ¦ Land possession is significantly incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-095 | P10002 | S-28456 | 3.01 | 1 | 0 | 0 | 38 | 34 | 0 | 100 | 50 | 45 |  |  | 50 | HIGH | Compensation completion is critically low ¦ Documentation is critically incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-096 | P10002 | S-63697 | 5.9 | 2 | 0 | 0 | 25 | 58 | 0 | 100 | 48 | 55 |  |  | 52 | HIGH | Compensation completion is critically low ¦ Documentation is partially completed ¦ Land possession is partially incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-097 | P10002 | S-59653 | 2.94 | 2 | 0 | 0 | 56 | 64 | 0 | 100 | 7 | 45 |  |  | 47 | MEDIUM | Compensation is only partially completed ¦ Land possession is significantly incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-098 | P10002 | S-38176 | 6.49 | 1 | 0 | 0 | 36 | 51 | 1 | 51 | 43 | 40 |  |  | 62 | HIGH | Compensation completion is critically low ¦ Documentation is partially completed ¦ R&R is partially completed ¦ Land possession is partially incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.
P10002-PL-099 | P10002 | S-49326 | 3.48 | 5 | 0 | 0 | 38 | 47 | 1 | 40 | 25 | 67 |  |  | 63 | HIGH | Compensation completion is critically low ¦ Documentation is partially completed ¦ R&R is partially completed ¦ Land possession is significantly incomplete | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify pending rehabilitation and resettlement requirements and create a time-bound completion plan. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker.
P10002-PL-100 | P10002 | S-23162 | 2.57 | 1 | 0 | 0 | 35 | 56 | 0 | 100 | 22 | 43 |  |  | 57 | HIGH | Compensation completion is critically low ¦ Documentation is partially completed ¦ Land possession is significantly incomplete ¦ Moderate stakeholder response | Review the pending compensation case, verify eligibility and documentation, and prioritize the case for payment. ¦ Conduct a document-gap review, identify missing documents and assign each pending document to the responsible officer. ¦ Identify the exact reason for pending possession and prioritize resolution after clearing the relevant blocker. ¦ Conduct targeted stakeholder follow-up, record unresolved concerns and track each issue until resolution.